Notewell AI ✦

NRES NEW MODELS SDA PROGRAMME

Reporting Resource Analysis

First-Time Setup vs Business-As-Usual Effort

For Programme Board | March 2026

| CENTRAL TEAM 52 hrs/mth BAU ongoing | PER PRACTICE 4-6 hrs/mth BAU ongoing | FIRST-TIME SETUP 80-100 hrs One-off per practice | HIGH WORKLOAD 4 reports Flagged below |
| --- | --- | --- | --- |

Executive Summary

This report provides detailed resource estimates for producing each mandatory ICB report throughout the NRES SDA pilot contract (£2.34M, 89,584 patients, 7 practices). It distinguishes between first-time setup effort (getting systems, templates, and processes in place) versus ongoing business-as-usual (BAU) effort once established. Updated March 2026 to align with the ICB Key Metrics Requirements Report v2 and the Comprehensive Reporting Plan v1.7, incorporating 48-week GPAD baseline data (561,294 appointments) and NARP/NCR system dependencies identified in the ICB feasibility assessment.

The analysis covers resource requirements for the central management team (Malcolm Railson, Amanda Palin) and each of the 7 GP practices. It identifies high-workload reports, data sources, and review/approval processes.

### Key Findings

- Central team (Railson/Palin) requires approximately 52 hours/month for BAU reporting coordination

- Each practice requires 4-6 hours/month for data provision and validation once established

- First-time setup requires 80-100 hours per practice (templates, processes, training, baseline data)

- 4 reports identified as HIGH WORKLOAD requiring significant effort: Mandatory Narrative, Part B Duration, Health Inequalities, Benefits Realisation

- Most data is extractable from clinical systems (SystmOne/EMIS) via Ardens Manager or standard reports — minimising manual effort

1. Monthly Reporting Requirements

| Report | Central Effort | Practice Effort | Data Source | Workload |
| --- | --- | --- | --- | --- |
| ACTIVITY & PERFORMANCE |  |  |  |  |
| Utilisation Rates by Practice | 2 hrs/mth | 30 mins/mth | SystmOne/EMIS appointment books — Ardens Manager extract | LOW |
| Unmet Demand (unable to book) | 1 hr/mth | 30 mins/mth | Clinical system — failed booking attempts / overflow queue | MEDIUM |
| Repeat Attendances (2+ in 4 wks) | 1 hr/mth | 15 mins/mth | Ardens Manager — patient activity report, auto-flagged | LOW |
| Access Times | 30 mins/mth | 15 mins/mth | Clinical system — appointment booked vs seen timestamps | LOW |
| Equity of Utilisation Index | 1.5 hrs/mth | N/A | Calculated centrally from practice data | LOW |
| Under-5 F2F Compliance | 30 mins/mth | 15 mins/mth | Ardens Manager — age filter on appointment mode | LOW |
| EMAS Referrals into NAS | 30 mins/mth | N/A | EMAS data feed — external agency (ambulance service) | LOW |
| Activity vs Targets | 2 hrs/mth | 30 mins/mth | Excel workbook V3.1 — auto-calculated from rota data | LOW |
| QUALITY & SAFETY |  |  |  |  |
| Complaints Tracker | 2 hrs/mth | 1 hr/mth | Practice complaints log — Practice Manager knowledge + Datix | MEDIUM |
| Safeguarding Referrals | 1 hr/mth | 30 mins/mth | Clinical system safeguarding codes + MASH referral records | MEDIUM |
| IPC Compliance | 1 hr/mth | 30 mins/mth | Hub site inspection records — Practice Manager sign-off | LOW |
| Incidents (LFPSE) | 1 hr/mth | 30 mins/mth | LFPSE system extract — Clinical Governance Lead | MEDIUM |
| FFT Results | 1 hr/mth | 30 mins/mth | FFT collection system — NHSE submission data | LOW |
| Mandatory Narrative | 4 hrs/mth | 1 hr/mth | Synthesised from above + Practice Manager knowledge | HIGH |
| REFERRALS & DIAGNOSTICS |  |  |  |  |
| Onward Referrals by Destination | 1.5 hrs/mth | 30 mins/mth | eRS extract + clinical system referral codes | MEDIUM |
| Direct Referral Compliance | 1 hr/mth | 30 mins/mth | eRS data — referrer ID analysis (NAS vs practice) | MEDIUM |
| Diagnostics Ordered | 1 hr/mth | 30 mins/mth | ICE/Order Comms pathology extract + imaging requests | LOW |
| 2WW Cancer Referrals | 30 mins/mth | 15 mins/mth | eRS 2WW pathway data — Cancer Alliance reporting | LOW |
| PRESCRIBING & MEDICINES |  |  |  |  |
| Formulary Compliance | 1.5 hrs/mth | 30 mins/mth | ePACT2 / OpenPrescribing — ICB Medicines Team data | LOW |
| NAS Prescribing Volume/Cost | 1 hr/mth | N/A | ePACT2 — prescriber-level analysis | LOW |
| Antibiotic Prescribing Rate | 30 mins/mth | N/A | ePACT2 — standard antibiotics dashboard | LOW |
| PART B COMPLEX CARE |  |  |  |  |
| Part B Appointment Duration | 2 hrs/mth | 45 mins/mth | Clinical system — SDA slot type duration vs planned | HIGH |
| ICB Priority: COPD/Asthma | 1.5 hrs/mth | 30 mins/mth | QOF registers + Ardens Manager LTC templates | MEDIUM |
| ICB Priority: RESPECT Plans | 1 hr/mth | 30 mins/mth | Clinical system RESPECT codes + Coordinate My Care | MEDIUM |
| Named GP Assignment | 1 hr/mth | 30 mins/mth | Clinical system — usual GP field for complex cohort | LOW |

|  | Monthly Total (BAU) Central Team: ~32 hours/month ¦ Per Practice: ~4-5 hours/month ¦ 7 Practices Total: ~28-35 hours/month |
| --- | --- |

2. Quarterly Reporting Requirements

| Report | Central Effort | Practice Effort | Data Source | Workload |
| --- | --- | --- | --- | --- |
| Financial Open Book Report | 6 hrs/qtr | 2 hrs/qtr | Excel workbook V3.1 + Finance Lead reconciliation | MEDIUM |
| Staff Satisfaction Survey | 4 hrs/qtr | 1 hr/qtr | Staff survey tool (e.g., SurveyMonkey) — HR coordination | MEDIUM |
| Staff Retention / Recruitment | 2 hrs/qtr | 1 hr/qtr | HR records — Practice Manager knowledge | LOW |
| Benefits Realisation Report | 8 hrs/qtr | 2 hrs/qtr | Multi-source synthesis — requires Programme Board input | HIGH |
| PAF Framework Compliance | 3 hrs/qtr | 30 mins/qtr | ICB Medicines Team — PAF dashboard data | LOW |
| Training & Placements Report | 2 hrs/qtr | 1 hr/qtr | Training Hub data + Practice Manager knowledge | LOW |
| Health Inequalities / Core20PLUS5 | 6 hrs/qtr | 2 hrs/qtr | IMD data, QOF registers, voluntary group liaison | HIGH |
| Part B Quarterly Review | 4 hrs/qtr | 1.5 hrs/qtr | Aggregation of monthly Part B data + clinical review | MEDIUM |

|  | Quarterly Total (BAU) Central Team: ~35 hours/quarter (add to monthly) ¦ Per Practice: ~11 hours/quarter (add to monthly) |
| --- | --- |

3. Annual Reporting Requirements

| Report | Central Effort | Practice Effort | Data Source | Workload |
| --- | --- | --- | --- | --- |
| Full Programme Evaluation (Y1 & Y2) | 40 hrs/yr | 8 hrs/yr | All sources — comprehensive synthesis for ICB/NHSE | HIGH |
| Innovator Site Learning Report | 16 hrs/yr | 4 hrs/yr | Programme Board knowledge + documented learnings | MEDIUM |
| DSPT Compliance Verification | 4 hrs/yr | 2 hrs/yr | DSPT toolkit — IG Lead | LOW |
| Insurance Certificate Verification | 2 hrs/yr | 1 hr/yr | Insurance documentation — Finance Lead | LOW |
| Business Continuity Plan Review | 4 hrs/yr | 2 hrs/yr | BCP documentation — Operations Manager | LOW |

|  | Annual Total (BAU) Central Team: ~66 hours/year (dedicated reporting weeks) ¦ Per Practice: ~17 hours/year |
| --- | --- |

4. First-Time Setup vs Business-As-Usual Comparison

The first 3-6 months of the programme require significantly higher effort to establish reporting templates, train staff, configure clinical system searches, and create baseline data. The table below shows the comparison.

| Activity | First-Time Setup | BAU (Ongoing) | Notes |
| --- | --- | --- | --- |
| CENTRAL TEAM ACTIVITIES |  |  |  |
| Report template creation | 40 hrs (one-off) | 0 | Word/Excel templates for all 25+ reports |
| Excel workbook V3.1 configuration | 20 hrs (one-off) | 2 hrs/mth maintenance | Formula setup, practice allocations, validation |
| Ardens Manager search configuration | 16 hrs (one-off) | 1 hr/mth updates | Custom searches for NAS activity reporting |
| Training materials development | 12 hrs (one-off) | 0 | Guides for practice managers |
| Practice training delivery | 14 hrs (one-off) | 0 | 2 hrs × 7 practices |
| Baseline data collection | 20 hrs (one-off) | 0 | Pre-go-live metrics for comparison |
| ICB reporting process agreement | 8 hrs (one-off) | 0 | Agree formats, timelines, submission routes |
| Review & approval workflow setup | 6 hrs (one-off) | 0 | Sign-off processes, escalation routes |
| CENTRAL FIRST-TIME TOTAL | 136 hrs | — |  |
| PER PRACTICE ACTIVITIES |  |  |  |
| Clinical system NAS slot type setup | 4 hrs (one-off) | 0 | SDA-prefixed appointment types |
| Ardens searches installation | 2 hrs (one-off) | 0 | Import central searches to local system |
| Named reporting lead nomination | 1 hr (one-off) | 0 | Partner decision, IG training |
| Training attendance | 2 hrs (one-off) | 0 | Attend central training session |
| First report dry-run | 4 hrs (one-off) | 0 | Practice submission with feedback |
| Baseline data verification | 3 hrs (one-off) | 0 | Confirm pre-go-live figures accurate |
| PER PRACTICE FIRST-TIME TOTAL | 16 hrs | — |  |
| ONGOING BAU COMPARISON |  |  |  |
| Central monthly reporting | — | 32 hrs/mth | Coordination, compilation, ICB submission |
| Central quarterly additions | — | 35 hrs/qtr | Deep-dive analysis, Board reports |
| Central annual additions | — | 66 hrs/yr | Full evaluation, innovator report |
| Per practice monthly | — | 4-5 hrs/mth | Data provision, validation |
| Per practice quarterly additions | — | 11 hrs/qtr | Survey completion, review participation |

| FIRST-TIME SETUP Central Team: 136 hours Per Practice: 16 hours × 7 = 112 hours TOTAL: ~248 hours (one-off) | BUSINESS AS USUAL (YEAR 1) Central: 32×12 + 35×4 + 66 = 590 hrs/yr Per Practice: (5×12)+(11×4)+(17) = 121 hrs/yr TOTAL: ~1,437 hours/year |
| --- | --- |

5. Data Source Reference Guide

Understanding where data comes from is critical for efficient reporting. The table below categorises data sources by type and indicates automation potential.

| Data Source | Type | Reports Using This Source | Automation |
| --- | --- | --- | --- |
| CLINICAL SYSTEM EXTRACTS |  |  |  |
| SystmOne appointment books | Automated report | Utilisation, Activity, Access Times, Part B Duration | HIGH |
| EMIS appointment books (GP Connect) | Automated report | Utilisation, Activity, Access Times, Part B Duration | HIGH |
| Ardens Manager searches | Semi-automated | Repeat attendance, Under-5 compliance, LTC registers, RESPECT | HIGH |
| QOF disease registers | Automated export | Part B cohorts, Health Inequalities, Priority groups | HIGH |
| Clinical coding (SNOMED) | Query-based | Safeguarding, Diagnostics, Referrals | MEDIUM |
| EXTERNAL NHS SYSTEMS |  |  |  |
| eRS (e-Referral Service) | NHS portal extract | Onward referrals, Direct referral %, 2WW cancer | MEDIUM |
| ePACT2 / OpenPrescribing | NHS portal extract | Prescribing volume/cost, Formulary, Antibiotics, PAF | HIGH |
| LFPSE (Patient Safety) | NHS portal extract | Incident reporting | MEDIUM |
| FFT collection system | NHS portal extract | Patient satisfaction | HIGH |
| DSPT toolkit | Annual submission | IG compliance verification | LOW |
| EXTERNAL AGENCY DATA |  |  |  |
| EMAS (ambulance service) | External feed | EMAS referrals into NAS | LOW |
| ICB Medicines Team | Supplied data | PAF scores, Formulary analysis | MEDIUM |
| Training Hub | Supplied data | Training placements, student feedback | LOW |
| Cancer Alliance | Supplied data | 2WW pathway outcomes | LOW |
| MASH (safeguarding) | External records | Safeguarding referral outcomes | LOW |
| NARP / Graphnet Lakehouse | ICB DDaT platform | A&E admissions, Patient Need Groups, hospital activity, health inequalities (via Tunde Adediran) | MEDIUM |
| NCR (Shared Care Record) | ICB DDaT platform | ReSPECT forms, cross-org patient contacts, End of Life cohort (via Katie Di Stefano) | MEDIUM |
| PRACTICE KNOWLEDGE / MANUAL |  |  |  |
| Practice Manager knowledge | Manual input | Complaints, IPC, Staff issues, Context narrative | NONE |
| Complaints log / Datix | Manual extract | Complaints tracker | LOW |
| Staff survey responses | Survey tool export | Staff satisfaction | MEDIUM |
| HR records | Manual review | Retention, Recruitment, Training | LOW |
| COMMUNITY / VOLUNTARY SECTOR |  |  |  |
| PPG (Patient Participation Group) | Liaison | Health inequalities insights, Patient feedback themes | NONE |
| Voluntary groups (Age UK, etc.) | Liaison | At-risk group access, Community intelligence | NONE |
| Social prescribing link workers | Liaison | Social prescribing referrals from NAS | LOW |

6. High Workload Reports — Detailed Breakdown

Four reports have been identified as requiring significantly more effort than others. These require dedicated time, multiple data sources, and synthesis skills. Programme Board should ensure adequate resource allocation.

### 6.1 Mandatory Narrative (Monthly)

| Aspect | Detail |
| --- | --- |
| Central Effort | 4 hours/month — synthesis, writing, review coordination |
| Practice Effort | 1 hour/month — provide context, validate interpretation |
| Data Sources | All monthly reports + Practice Manager knowledge + Clinical Governance input |
| Why High Workload | Requires interpretation, not just data. Must explain variances, document actions, evidence learning. Cannot be automated. |
| Review Process | Draft by Programme Manager → Clinical Lead review → Practice Manager validation → Programme Board sign-off |
| Mitigation | Create standard narrative templates with prompts. Gather practice feedback systematically throughout month. |

### 6.2 Part B Appointment Duration Monitoring (Monthly)

| Aspect | Detail |
| --- | --- |
| Central Effort | 2 hours/month — extract, analyse, identify outliers |
| Practice Effort | 45 mins/month — validate duration data, explain anomalies |
| Data Sources | Clinical system appointment duration fields (actual vs planned) for SDA-prefixed slot types |
| Why High Workload | Duration data often incomplete or requires manual calculation. Must distinguish genuine variation from recording issues. |
| Review Process | Data extract → Outlier identification → Practice query → Clinical Lead review → Monthly report inclusion |
| Mitigation | Ensure clinical systems configured to capture actual appointment end time. Train clinicians on correct recording. |

### 6.3 Health Inequalities / Core20PLUS5 (Quarterly)

| Aspect | Detail |
| --- | --- |
| Central Effort | 6 hours/quarter — multi-source synthesis, IMD analysis, equity calculations |
| Practice Effort | 2 hours/quarter — provide local intelligence, at-risk group identification |
| Data Sources | IMD postcode lookup, QOF registers, PPG feedback, voluntary group liaison, interpreter service data |
| Why High Workload | ICB detailed metrics not yet confirmed. Requires linking patient data to deprivation indices. Community liaison is manual. |
| Review Process | Data compilation → IMD linkage → Practice review → Programme Board discussion → ICB submission |
| Mitigation | Request ICB clarity on required metrics. Establish routine PPG/voluntary sector liaison points. Use Ardens population health tools. |

### 6.4 Benefits Realisation Report (Quarterly)

| Aspect | Detail |
| --- | --- |
| Central Effort | 8 hours/quarter — methodology application, benefit tracking, baseline comparison |
| Practice Effort | 2 hours/quarter — provide operational benefits evidence, staff feedback |
| Data Sources | All operational data + Finance data + Staff feedback + Patient feedback + Strategic goals tracking |
| Why High Workload | Requires benefits realisation methodology. Must track cashable and non-cashable benefits against baseline. Subjective elements. |
| Review Process | Benefits framework application → Draft report → Finance Lead review → Programme Board discussion → ICB submission |
| Mitigation | Establish clear benefits categories and measurement methodology in Month 1. Create benefits tracking dashboard. |

7. Review & Approval Processes

### 7.1 Monthly Report Review Workflow

| Stage | Owner | Effort | Timeline | Output |
| --- | --- | --- | --- | --- |
| 1. Data extraction | Programme Manager | 8 hrs | Days 1-3 | Raw data files from all sources |
| 2. Data validation | Practice Managers (×7) | 30 mins each | Days 3-5 | Confirmed/corrected data |
| 3. Report compilation | Programme Manager | 6 hrs | Days 5-6 | Draft monthly report |
| 4. Narrative drafting | Programme Manager | 4 hrs | Day 6 | Mandatory narrative section |
| 5. Clinical review | Clinical Lead | 2 hrs | Day 7 | Clinical accuracy sign-off |
| 6. Quality review | Quality Lead | 1 hr | Day 7 | Quality metrics sign-off |
| 7. Finance review | Finance Lead | 1 hr | Day 8 | Financial data sign-off |
| 8. Final approval | Programme Board Chair | 1 hr | Day 8-9 | Approved for submission |
| 9. ICB submission | Programme Manager | 30 mins | Day 10 | Submitted to ICB |

### 7.2 Quarterly Report Additional Steps

| Stage | Owner | Effort | Timeline | Output |
| --- | --- | --- | --- | --- |
| 1. Staff survey deployment | HR Lead | 2 hrs | Week 1 of quarter | Survey sent to all NAS staff |
| 2. Survey analysis | Programme Manager | 3 hrs | Week 2 | Satisfaction scores, themes |
| 3. Benefits tracking | Programme Manager | 4 hrs | Week 2 | Benefits realisation update |
| 4. Finance deep-dive | Finance Lead | 4 hrs | Week 2 | Open book financial pack |
| 5. Practice review meetings | Programme Manager + PMs | 14 hrs total | Week 3 | Practice-level insights |
| 6. Programme Board paper | Programme Manager | 4 hrs | Week 3 | Board paper with recommendations |
| 7. Board approval | Programme Board | 2 hrs | Board meeting | Approved quarterly submission |

8. Practice-Level Resource Summary

| Practice | List Size | First-Time Setup | Monthly BAU | Quarterly Add | Annual Total |
| --- | --- | --- | --- | --- | --- |
| The Parks MC | 22,827 | 16 hrs | 5 hrs | 11 hrs | ~121 hrs |
| Brackley MC | 16,212 | 16 hrs | 5 hrs | 11 hrs | ~121 hrs |
| Springfield Surgery | 12,611 | 16 hrs | 4.5 hrs | 11 hrs | ~115 hrs |
| Towcester MC | 11,748 | 16 hrs | 4.5 hrs | 11 hrs | ~115 hrs |
| Bugbrooke Surgery | 10,788 | 16 hrs | 4 hrs | 11 hrs | ~109 hrs |
| Brook Health Centre | 9,069 | 16 hrs | 4 hrs | 11 hrs | ~109 hrs |
| Denton Village | 6,329 | 16 hrs | 4 hrs | 11 hrs | ~109 hrs |
| TOTAL (7 practices) | 89,584 | 112 hrs | ~31 hrs/mth | ~77 hrs/qtr | ~799 hrs/yr |

|  | Practice Manager Time Commitment Each Practice Manager should expect to commit approximately 4-6 hours per month to NRES reporting once established, with an additional 11 hours per quarter for deeper reviews. This is primarily data validation and context provision — the central team handles compilation and ICB submission. |
| --- | --- |

Document Control

| Property | Value |
| --- | --- |
| Document Title | NRES Reporting Resource Analysis |
| Version | 1.0 |
| Date | March 2026 |
| Author | Malcolm Railson, Digital & Transformation Lead |
| Status | For Programme Board |
| Next Review | Post go-live (May 2026) |