# NRES New Models SDA Pilot

Comprehensive Reporting Plan

Rural East & South Neighbourhood Access Service

88,938 Patients | 7 GP Practices | £2.34M Contract

| Document Owner: | NRES Programme Board |
| --- | --- |
| Version: | 1.2 |
| Date: | December 2025 |
| Status: | For ICB/Programme Board Approval |
| Classification: | Official – Sensitive |

# 1. Executive Summary

This Reporting Plan establishes the framework for monitoring, evaluating and reporting on the NRES New Models Same Day Access (SDA) pilot. The plan is designed to meet Northamptonshire ICB's requirements for oversight, assurance and value-for-money assessment of the £2.34M investment.

The reporting framework utilises the slot types configured in the clinical system: NRES SDA Face 2 Face and NRES SDA Virtual, with associated rota types NRES SDA GP and NRES SDA ANP to enable granular analysis of service delivery, workforce deployment and patient outcomes.

# 2. Scope & Objectives

## 2.1 Reporting Objectives

- Demonstrate compliance with contractual obligations and NHS standards

- Provide ICB with transparent oversight of service performance and financial expenditure

- Enable evidence-based decision making for service optimisation

- Support pilot evaluation and business case development for future commissioning

- Identify variation across practices to share best practice and address underperformance

## 2.2 Risk Stratification & Continuity of Care

A key innovation in the NRES SDA pilot is the integration of Risk Stratification Flag updates to intelligently filter patients between Same Day Access and Continuity of Care pathways. This ensures clinically appropriate routing while maximising the efficiency of SDA capacity.

Risk Stratification Approach:

- RED Flag Patients: High-risk patients (frailty, complex multi-morbidity, palliative care, frequent attenders with complex needs) will be automatically filtered to Continuity of Care pathways with their named/usual GP rather than being routed to SDA slots

- AMBER Flag Patients: Moderate-risk patients may access SDA for acute presentations but will be flagged for care coordinator review to determine if continuity arrangements are required

- GREEN Flag Patients: Lower-risk patients are appropriate for standard SDA routing for acute same-day presentations

This stratification will be implemented through clinical system alerts and booking workflows, with the Risk Stratification Flag visible to reception and clinical staff at point of contact. Reporting will track the effectiveness of this filtering approach in maintaining continuity for vulnerable patients while optimising SDA utilisation.

## 2.3 Clinical System Interoperability

The NRES footprint comprises 5 SystmOne practices and 2 EMIS practices. Cross-practice booking and data sharing is enabled through two pathways:

- SystmOne to SystmOne (Hub Model): The 5 SystmOne practices book directly into the SystmOne-hosted hub, providing seamless data connectivity within the same clinical system type. This enables full record visibility, real-time slot availability, and integrated clinical documentation.

- GP Connect (Cross-System): The 2 EMIS practices utilise GP Connect for cross-clinical system booking into the SystmOne hub. This NHS Digital standard enables appointment booking across system boundaries while maintaining appropriate data sharing and clinical safety standards.

Reporting will track booking volumes and any technical issues by connectivity type to identify any differential performance or access barriers between the two pathways.

## 2.4 Data Sources

- Clinical system appointment data (SystmOne hub + GP Connect feeds)

- Risk Stratification Flag register and updates

- Staff rotas and session logs (NRES SDA GP / NRES SDA ANP)

- Patient feedback surveys

- Financial records and invoicing data

- Outcome coding and onward referral data

# 3. Key Performance Indicator Framework

The following KPIs are aligned with NHS England's Primary Care Access standards and ICB commissioning requirements.

## 3.1 Access & Utilisation Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| Slot Utilisation Rate | Booked appointments ÷ Available slots × 100 | ≥85% | Weekly |
| DNA Rate | Did Not Attend ÷ Total Booked × 100 (by F2F/Virtual) | <5% | Weekly |
| Same Day Access Rate | Appointments booked & attended same day ÷ Total | ≥70% | Weekly |
| Mode Split (F2F:Virtual) | Distribution between Face 2 Face and Virtual slots | Monitor | Weekly |
| Time to Appointment | Means hours from booking request to appointment | <4 hours | Weekly |

## 3.2 Clinical System Connectivity Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| SystmOne Booking Rate | % of bookings via SystmOne direct (5 practices) | Monitor | Weekly |
| GP Connect Booking Rate | % of bookings via GP Connect (2 EMIS practices) | Monitor | Weekly |
| GP Connect Success Rate | Successful GP Connect transactions ÷ Attempts | ≥98% | Weekly |
| Cross-System DNA Variance | DNA rate difference: GP Connect vs SystmOne direct | <2% | Monthly |

## 3.3 Risk Stratification & Continuity Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| RED Flag Continuity Rate | % of RED flag patients seen by named/usual GP | ≥80% | Monthly |
| RED Flag SDA Diversion | RED flag patients incorrectly routed to SDA | <10% | Weekly |
| Risk Flag Currency | % of registered patients with up-to-date risk stratification | ≥95% | Monthly |
| Stratification Override Rate | Clinician overrides of automated routing | Monitor | Weekly |
| AMBER Review Completion | % of AMBER patients reviewed by care coordinator | ≥90% | Monthly |

## 3.4 Workforce & Capacity Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| GP Sessions Delivered | Total GP rota sessions completed vs planned | ≥95% | Weekly |
| ANP Sessions Delivered | Total ANP rota sessions completed vs planned | ≥95% | Weekly |
| Skill Mix Ratio | GP appointments: ANP appointments | Monitor | Monthly |
| Unfilled Sessions | Planned sessions with no clinician assigned | <5% | Weekly |

## 3.5 Quality & Outcomes Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| Patient Satisfaction | FFT positive response rate | ≥90% | Monthly |
| Consultation Outcome Rate | % resolved at SDA vs requiring follow-up | ≥75% | Monthly |
| Onward Referral Rate | Referrals to secondary care from SDA appointments | Monitor | Monthly |
| Safety Events | Significant events / incidents linked to SDA service | 0 | Immediate |

## 3.6 Financial Metrics

| KPI | Definition | Target | Frequency |
| --- | --- | --- | --- |
| Cost per Appointment | Total expenditure ÷ Completed appointments | Monitor | Monthly |
| Budget Variance | Actual spend vs profiled budget | ±5% | Monthly |
| Activity vs Contract | Delivered appointments vs contracted volumes | ≥95% | Monthly |
| Cost per Mode | Comparative cost: F2F vs Virtual delivery | Monitor | Quarterly |

# 4. Reporting Schedule & Governance

## 4.1 Report Types & Frequency

| Report | Audience | Frequency | Owner |
| --- | --- | --- | --- |
| Operational Dashboard | Practice Managers, PCN Team | Real-time / Daily | NRES Development Manager |
| Weekly Activity Report | Programme Board, Practices | Weekly (Monday) | NRES Development Manager |
| Monthly Performance Report | ICB, Programme Board | Monthly (by 10th) | Programme Board Chair |
| Quarterly Evaluation Report | ICB Board, NHS England | Quarterly | Programme Board |
| Annual Review & Business Case | ICB, NHS England, Commissioners | Annually | Programme Board |

## 4.2 Escalation Thresholds

The following triggers will initiate escalation to the Programme Board and/or ICB:

- RED: Slot utilisation <70% for 2 consecutive weeks

- RED: DNA rate >10% for 2 consecutive weeks

- RED: Any patient safety incident

- AMBER: Budget variance >10%

- AMBER: Unfilled sessions >10%

- AMBER: Patient satisfaction <85%

# 5. Detailed Report Specifications

## 5.1 Weekly Activity Report

Purpose: Operational oversight and early identification of issues

Content:

- Total appointments by slot type (NRES SDA Face 2 Face / NRES SDA Virtual)

- Appointments by rota type (NRES SDA GP / NRES SDA ANP)

- Booking source analysis (SystmOne direct vs GP Connect)

- Utilisation rate per practice

- DNA rates by mode and practice

- Same day booking rate

- Unfilled slot analysis

- Week-on-week trend comparison

- Risk Stratification routing summary (RED/AMBER/GREEN flag patient flows)

- RED flag patients routed to SDA – clinical justification review

- Exception report and actions

## 5.2 Monthly Performance Report

Purpose: ICB assurance and Programme Board decision-making

Content:

- Executive summary with RAG status

- Full KPI dashboard with targets vs actuals

- Practice-level breakdown and variation analysis

- Mode analysis: F2F vs Virtual performance comparison

- Workforce analysis: GP vs ANP activity and outcomes

- Risk Stratification effectiveness: continuity rates for RED flag patients

- Financial summary: spend vs budget, cost per appointment

- Patient feedback summary

- Demand patterns: time of day, day of week analysis

- Risk register update

- Recommendations and improvement actions

## 5.3 Quarterly Evaluation Report

Purpose: Strategic evaluation and NHS England reporting

Content:

- Cumulative performance against all KPIs

- Risk Stratification impact assessment: outcomes for RED flag patients (continuity vs SDA)

- Trend analysis and forecasting

- Patient cohort analysis (demographics, presenting conditions)

- Impact assessment on core GP access

- Comparative analysis across 7 practices

- Value for money assessment

- Lessons learned and best practice sharing

- Recommendations for service modification

# 6. Sample Dashboard Views

The following illustrates the key dashboard views that will be generated from the slot type and rota data.

## 6.1 Slot Type Analysis View

| Slot Type | Available | Booked | Attended | DNA | Util % |
| --- | --- | --- | --- | --- | --- |
| NRES SDA Face 2 Face | 450 | 412 | 398 | 14 | 91.6% |
| NRES SDA Virtual | 350 | 301 | 287 | 14 | 86.0% |
| TOTAL | 800 | 713 | 685 | 28 | 89.1% |

## 6.2 Rota Type Analysis View

| Rota Type | Sessions | Appts | Avg/Session | DNA Rate | Cost/Appt |
| --- | --- | --- | --- | --- | --- |
| NRES SDA GP – F2F | 45 | 225 | 5.0 | 3.1% | £48.20 |
| NRES SDA GP – Virtual | 30 | 180 | 6.0 | 4.4% | £38.50 |
| NRES SDA ANP – F2F | 35 | 173 | 4.9 | 4.0% | £32.10 |
| NRES SDA ANP – Virtual | 25 | 121 | 4.8 | 5.0% | £28.40 |

## 6.3 Clinical System Connectivity View

| Booking Source | Practices | Bookings | Success % | DNA Rate | RAG |
| --- | --- | --- | --- | --- | --- |
| SystmOne Direct (Hub) | 5 | 523 | 100% | 3.6% | GREEN |
| GP Connect (EMIS) | 2 | 190 | 98.4% | 4.2% | GREEN |
| TOTAL | 7 | 713 | 99.5% | 3.8% | GREEN |

## 6.4 Risk Stratification Routing View

| Risk Flag | Total Pts | SDA Route | Continuity | Correct % | RAG |
| --- | --- | --- | --- | --- | --- |
| RED | 847 | 72 | 775 | 91.5% | GREEN |
| AMBER | 2,341 | 1,892 | 449 | N/A | GREEN |
| GREEN | 5,124 | 4,987 | 137 | N/A | GREEN |

Note: RED flag patients routed to SDA represent those with acute presentations where SDA was clinically appropriate (e.g., acute infection in palliative patient). These are reviewed weekly to ensure routing decisions are clinically justified.

## 6.5 Practice Comparison View

| Practice | Total Appts | Utilisation | DNA Rate | RAG |
| --- | --- | --- | --- | --- |
| Practice A | 142 | 94.2% | 2.8% | GREEN |
| Practice B | 118 | 88.4% | 4.2% | GREEN |
| Practice C | 95 | 78.3% | 6.1% | AMBER |
| Practice D | 87 | 68.2% | 8.4% | RED |

# 7. Data Governance & Quality

## 7.1 Data Quality Standards

- All appointments must be coded with correct slot type at point of booking

- Rota allocation must match clinician type (GP/ANP)

- Outcome codes to be recorded within 24 hours of consultation

- Weekly data quality audits by PCN team

- Monthly validation against source systems

## 7.2 Information Governance

- All reports to comply with NHS Data Security and Protection Toolkit requirements

- Patient-level data pseudonymised or aggregated for reporting

- Reports stored on secure NHS network with appropriate access controls

- Data sharing agreements in place between practices and PCN

# 8. Appendices

The following supporting documents are available on request:

- Appendix A: Slot Type Configuration Technical Specification

- Appendix B: Rota Type Mapping and Clinical Coding Guide

- Appendix C: Report Template Examples

- Appendix D: Data Quality Audit Checklist

- Appendix E: Glossary of Terms

# 9. Document Approval

| Role | Name | Date | Signature |
| --- | --- | --- | --- |
| NRES Development Manager |  |  |  |
| Programme Board Chair |  |  |  |
| ICB Representative |  |  |  |
| Clinical Lead |  |  |  |

Document Control: This document will be reviewed quarterly and updated as the pilot evolves. Any changes to KPIs or reporting requirements must be approved by the Programme Board.