| Minutes of Programme Board for SDA SDA Innovator Site (Rural South and East) Brackely Medical Centre, Conference Room- 23/12/2025 Members:. Tina Beardsworth (TB); Brackley Medical Centre; Simon Ellis (SEl); Towcester Medical Centre. Sandra Easton (SaE); Brackley Medical Centre; Chloe Lamont (CL); Towcester Medical Centre. Amanda Taylor (AT); Brackley Medical Centre; David Wade (DW); Denton Village Surgery. Rachel Parry (RP); Bugbrooke Medical Practice; Nicola Draper (ND); Denton Village Surgery. William Hunt (WH); Bugbrooke Medical Practice; Amy Amin (AA); Denton Village Surgery. Lorraine Spicer (LSp); Bugbrooke Medical Practice; Arif Supple (AS); The Brook Health Centre. Lucy Hibberd (LH); Bugbrooke Medical Practice; Anita Carter (AC); The Brook Health Centre. Dal Samra (DS); Springfield Surgery; Malcolm Railson (MR); Brackley and Towcester. Hayley Willingham (HW); Springfield Surgery; Michael Chapman (MCh); Northants ICB. Uzra Nazir (UN); The Parks; Ellie Wagg (EW); Northants ICB. Alexander Whitehead (AW); Danes Camp Medical Centre; Helen Barrett (HB); Social Action. Charlotte Barnell (CB); The Parks; Anshal Pratyush. PML Representatives:. Mark Gray (MG); Medical Director; Anshal Pratyush (AP); Project Support Officer. Maureen Green (MJG); Director of Community Services; Chloe Thorpe (CT); Personal Assistant. Carolyn Abbisogni (CA); Chief Executive Officer; Claire Garbett (CG); Executive Assistant. John Harrison (JH); Co-Chair; Co-Chair; Claire Garbett (CG); Executive Assistant. Apologies for Today’s Meeting: Carolyn Abbisogni, John Harrison, Arif Supple, Claire Garbett, William Hunt, David Wade, Michael Chapman. |
| --- |
| Agenda Item | Action |
| Welcomes made - MJG confirms everyone is happy with the meeting being recorded. - Previous minutes circulated-everyone in agreement and happy that they are accurate. - MJG highlighted the departure of Ellie Wagg from the ICB and welcomed Helen Barrett - An action was noted that some people share the same initials- CG has actioned this. Apologies - Apologies for today’s meeting were noted as above Terms of Reference - Everyone in agreement with the ToR- they were attached the to the email trail Risk Register – circulated separately for initial agreement of risks - The risk register was reviewed, with recruitment identified as a critical, high-impact risk. - Other identified risks are not high risks currently - MJG asked that MR and AT meet with her week commencing 5th January to review the risk register-MJG to action Finance - Grant application- MJG did on behalf of SDA board, Carlolyn is in the process of signing. 30k funding to be used between December 2025- March 2026 at the next face-to-face meeting due to take place at the end of January- MJG will have an update Recruitment Strategy: - Job adverts shown to the meeting- asked for any feedback to be passed to MR who will action - It was highlighted that advertisement for the GP and ANP jobs needs to be imminent to ensure that the job roles are filled by April 1st - Discussions around the £11,000 per session- the meeting came to agreement that this is reasonable - The need for staff (8 full-time GPs and 6.9 ACPs) was acknowledged, with concerns about achieving these numbers by 1st April. - The mode of employment was discussed whether it will be through PML or individual practices - It was noted by multiple attendees that GPs performing only SDA work could lead to de-skilling. - Advertisements should be generic primary care GP/ACP roles, highlighting involvement in a pilot scheme, with permanent contracts offered - GP adverts will be advertised before Christmas (on indeed), ANP adverts will be out by the end of January- MR to action Hub and Spoke Model - Two primary hubs are currently identified- The Parks and Brackley Medical Centre- this is yet to be confirmed. MR can confirm by 15th January - The Brook health center is considered a spoke site, with potential for future hub status pending mid-January discussions. - A target date of mid-January was set for an update on hub/spoke decisions, with further discussion scheduled for the Programme Board Teams meeting on Tuesday 15th January. - Concerns were raised about the lack of funding for converting non-medical facilities into clinical sites due to specific equipment requirements and clinical specifications. - A 50% split for face to face appointments vs virtual appointments is considered to be the general mix of patient contacts. - Non-GMS space is being considered Same Day Access Vault Pilot Presentation (Malcolm): - MR provided an overview of the SDA Vault, which formulates information from various sources into a central dashboard using AI technology. - The tool has received pilot approval, with the current version not using patient-identifiable data. - Initial feedback on the pilot interface and functionality is requested. - The SDA Vault is designed as a business tool to enhance efficiency, with future integration planned for EMIS and System 1. It holds MHRA Class 1 medical device approval. - All attendees were sent a link to login and view the vault - CT was sent the pilot approval Patient Participation Group (PPG) Protocol: - Significant interest from PPG members was noted. - A process is required to manage participation, with a suggestion for a Teams meeting to allow all interested parties to contribute, and then for practices to nominate 2-3 representatives for broader workshops. TBC who is to follow up - Practice managers will be responsible for the nomination of a PPG. Insurance Approach: - Significant insurance costs are anticipated for the agreement. AT will liaise with practice managers to investigate options (PML process, separate cover). AT to action AOB: None brought to attention | MJG MJG MR MR MR AT |
| Next Meeting: Virtual Meeting- 13th January 13:00-14:00 |  |