WORKFORCE RECRUITMENT, CONTRACTS, AND ENHANCED ACCESS IMPLEMENTATION PLANNING

MEETING DETAILS

| Date | Thursday 8th January 2026 |
| --- | --- |
| Time | 11:45 GMT |
| Location | Face to Face at PML Bicester with MJG remote via Teams |
| Attendees | Dr Mark Gray, Dr Muhammad Chishti, Maureen Green, Amanda Taylor, Malcolm Railson |

EXECUTIVE SUMMARY

This meeting focused on the progress of workforce recruitment for Enhanced Access, contractual arrangements, and operational considerations for new models of care. Key discussions revolved around the status of job adverts, interview processes, and the exploration of locum services like Lantum. Significant attention was given to the complexities of clinician employment contracts, liability, and equitable resourcing across practices, particularly in the context of hub-and-spoke models and the integration of IT systems. The session also addressed ongoing risks, particularly regarding ICE Access and the evolving landscape of neighbourhood-based care models, whilst confirming financial updates and resource transparency mechanisms.

Key Points

- GMS Contract and MOUs: The GMS contract is currently under review by Hempsons. An MOU between the SNO and the ICB is being developed, which will be accessible via a dashboard once signed. A template for an MOU between the practices and the SNOfrom the ICB was received and requires refinement before wider circulation. The final operating model context is important for these documents.

- Workforce Recruitment Status:

- Job adverts for clinical roles are closing on 20th January, with interviews scheduled for 27th January. These adverts are placed on NHS Jobs and Indeed.

- The interview panel is expected to include clinical and managerial representation.

- Consideration was given to keeping job adverts open continuously to attract a wider pool of candidates due to the 'numbers game' of recruitment.

- The use of Physician Associates (PAs) for these roles was discussed, with a consensus not to utilise them for differentiated tasks or prescribing duties, aligning with current regulatory positions and PCN policies.

- Locum and Sessional Workforce:

- The possibility of using locums, and platforms such as Lantum and NASGP, was explored to supplement substantive staff, particularly if financial allowances permit.

- Lantum is engaging with Wellingborough and offering a 2% fee structure (rate plus 2%). NASGP's fee is deducted from the clinician's wages, making it free for practices.

- Rates for GPs were noted to be around £85 per hour, with a 2% premium for platform usage.

- Clinician Contracts and Liability:

- A universal, fixed-term contract template is desired for clinicians, given the non-guaranteed nature of funding. The ICB had previously alluded to providing template wording for mitigation against redundancy claims but now recommends seeking HR and legal advice.

- Discussion on liability elements, particularly for limited companies versus unlimited GMS partnerships, remains unresolved.

- The fair and equitable resourcing across practices for employed clinicians, considering the "first come, first served" nature of appointment booking, is a key concern.

- Hub and Spoke Model Implementation:

- The development of a hub-and-spoke model is progressing, with Brackley, Parks, and potentially Brook being considered as central hubs. Towcester has indicated it lacks space.

- A meeting by 15th January will finalise Brook's participation.

- A travel time matrix between practices has been developed to inform clinician deployment.

- The less a clinician works across multiple practices initially, the better for consistency, especially given different clinical systems.

- IT and Digital Integration:

- The remote booking process, similar to the ARI hub and GPA models, is understood and in use for Enhanced Access appointments.

- System 1 practices will use the Hub version for rota management. EMIS practices will use GP Connect, which is noted to be more efficient for EMIS to System 1 booking than the reverse.

- Mapping slot types for consistent reporting to the ICB and Programme Board has been completed.

- Access to clinical systems and data sharing agreements are in place for key personnel to run reports and manage appointment slots.

- Test Results and Referrals Management:

- Managing test results and referrals within the Enhanced Access model is a high-risk item.

- The current consensus and legal understanding is that the requesting clinician should manage the results within the patient's practice clinical system.

- Concerns exist regarding ICE Access, including licence costs, restrictions, and the need for ICB intervention to ensure smooth adoption.

- ICB and NHS England Organisational Changes:

- Acknowledged ongoing changes within the ICB and NHS England, including potential mergers and staff reductions.

- These changes are not expected to directly impact the Enhanced Access operational plans as the spec and funding are agreed.

- Financial and Tracking Transparency:

- An hours tracker has been implemented in Notewell to log time spent on various project activities for increased transparency (optional at this time).

- The £30,000 funding from the ICB for certain activities was received on Tuesday, and an opening/closing balance will be provided.

NEXT MEETING

MS Teams meeting next week (13th Jan 2026 at 13:00 Via Teams)

ACTION ITEMS

| Action | Owner | Deadline | Priority | Status |
| --- | --- | --- | --- | --- |
| Circulate refined MOU template to practices for review and update on full MOU from PML | MG | ASAP | HIGH | ○ Open |
| Finalise interview panel members for clinical roles | MG | ASAP | HIGH | ○ Open |
| Review option of keeping job adverts open continuously | MG | By Next Meeting | LOW | ○ Open |
| Agree rates and platform selection for locum services Board (By Next Meeting) | Programme Board | Lantum/NASGP | MEDIUM | ○ Open |
| Develop a process for fair and equitable resourcing of clinicians across practices | MG | End of Month | MEDIUM | ○ Open |
| Confirm Brook's participation as a hub | MR | 15th January 2026 | HIGH | ○ Open |
| Resolve ICE Access licensing costs and restrictions and ICB | MR | End of Month | HIGH | ○ Open |
| Discuss host organisation and clinician employment approaches at the next board meeting Board | Programme Board | Next Board Meeting | HIGH | ○ Open |
| Obtain an update from Alex regarding insurance provisions from The Parks | AT | By Next Meeting | MEDIUM | ○ Open |
| Further investigate professional indemnity components | AT | By Next Meeting | MEDIUM | ○ Open |
| Meet with Tracy Dempster/Helen Barrett to discuss voluntary sector engagement, | MG, AT, MR, MJG Tentative | 19 Jan 2026 | MEDIUM | ○ Open |