| Minutes of Programme Board for SDA SDA Innovator Site (Rural South and East) On Teams - 09/12/2025 Members:. Tina Beardsworth (TB); Brackley Medical Centre; Simon Ellis (SEl); Towcester Medical Centre. Sandra Easton (SaE); Brackley Medical Centre; Chloe Lamont (CL); Towcester Medical Centre. Amanda Taylor (AT); Brackley Medical Centre; David Wade (DW); Denton Village Surgery. Rachel Parry (RP); Bugbrooke Medical Practice; Nicola Draper (ND); Denton Village Surgery. William Hunt (WH); Bugbrooke Medical Practice; Amy Amin (AA); Denton Village Surgery. Lorraine Spicer (LSp); Bugbrooke Medical Practice; Arif Supple (AS); The Brook Health Centre. Lucy Hibberd (LH); Bugbrooke Medical Practice; Anita Carter (AC); The Brook Health Centre. Dal Samra (DS); Springfield Surgery; Malcolm Railson (MR); Brackley and Towcester. Hayley Willingham (HW); Springfield Surgery; Michael Chapman (MCh); Northants ICB. Muhammed Chishti (MuC); The Parks; Ellie Wagg (EW); Northants ICB. Alexander Whitehead (AW); Danes Camp Medical Centre. Charlotte Barnell (CB); The Parks; Anshal Pratyush. PML Representatives:. Mark Gray (MG); Medical Director; Anshal Pratyush (AP); Project Support Officer. Maureen Green (MJG); Director of Community Services; Chloe Thorpe (CT); Personal Assistant. Carolyn Abbisogni (CA); Chief Executive Officer; Claire Garbett (CG); Executive Assistant. John Harrison (JH); Co-Chair; Co-Chair; Claire Garbett (CG); Executive Assistant. Apologies for Today’s Meeting: Carolyn Abbisogni, John Harrison, William Hunt, Chloe Lamont, Amy Amin, Arif Supple.. |
| --- |
| Agenda Item | Action |
| - Welcome to the Meeting - Mark Gray (MG) welcomed everyone to the meeting, Maureen has been delayed but was hoping to join the meeting shortly. - Previous minutes, finalised terms of reference and today’s agenda were circulated within the Teams invite. - MG introduced Anshal Pratyush, Project Support Officer, who would be providing project support as well as timelines for the proposed work. Chloe Thorpe, PA at PML was also introduced who will be providing administrative support for the Programme Board. - Minutes were agreed noting the following: Sandra Easton (SaE) raised that she and Simon Ellis (SEl) have the same initials; Claire clarified this will be changed going forward. ACTION: CG - Apologies - Apologies for today’s meeting were noted from MJG as well as CA, JH, WH, CL, AA, AS. - Terms of Reference for ratification - SaE said there was some mistakes on it and she had highlighted it to MJG but has not had a response yet. - There was discussion around the PPG involvement as in total, there could be 8 PPGs involved. MG asked EW if Wellingborough innovator site have a patient representative and a voluntary sector on their Board? EW confirmed that Wellingborough have both she also highlighted the importance of having these. MG asked if everyone was happy with this, highlighting that some people had concerns about this in the last meeting. It was agreed that both the patient and voluntary sector representatives would be non-voting board members. Terms of Reference will be changed to reflect this. ACTION: MJG/MG - RP asked how many people from the voluntary sector would be added and who would they be. MG stated he doesn’t think that there should be more than two representatives on the Board and asked for the attendees’ opinions on that. There was a discussion about the possibility of a rotation but an element of continuity would be preferable. It was agreed that there should be a small number and agreement that the PPG leads be contacted. MG confirmed he would contact the PPG Leads and will give them a list of what is needed and asking them to nominate two PPG representatives who could then represent that group. ACTION: MG to follow up. - Terms of Reference will be changed to reflect the above and recirculated to everyone when done. ACTION: MJG - Risk Register – circulated separately for initial agreement of risks - This is still being compiled. - Finance - MG noted the specifications of the £30,000 development fund available to all the leads. The ask was that all invoices are sent to PML Fnance Department email (pml.finance@nhs.net). MG asked EW for clarity on whether non-clinician backfill and clinical backfill would be paid. EW confirmed it can be used for both and will circulate the agreed rates. EW also highlighted that she will need an outline plan on how the £30,000 grant will be spent before finalisation; MJG is filling out the application currently. ACTION: EW - Appointment modelling and recruitment for SDA cover: MG asked the meeting how they would feel about PML recruiting for a neighbourhood team rather than individual practices employing staff. SE highlighted that all options of employment need discussing, he has asked for information on this arrangement before deciding. SE also asked that this is a priority and gets to him before next week, the overheads from PML and PCN being 7% would also need clarifying whether these would be applied. It was noted that when you move a GP over 2 or more practices they feel ‘less at home’. Once all the practices have the information they can make a decision and let MG know. ACTION: MG - MG highlighted that this is a neighbourhood project rather than a practice project; anyone hired would need to be comfortable working across the neighbourhood. EW clarified that the agreed specification was to see patients across all of the practices. MuC has noted that he shares the same concerns as his colleagues and highlighted the issues if one person works across different practices they could be exposed to more clinical risk compared to staying in one practice. An agreement cannot be made without having the information as it is difficult to make a final decision. - It was agreed that MG will look at what overheads would be taken from the employment contracts. MuC agreed to look at relevant adverts for GP’s, Paramedics and ANPs to compile job descriptions. ACTION: MuC. - In terms of digital support, EW clarified a digital team was available from the ICB to help with any digital challenges that might be presented. Hub and Spoke Model: - Hub v Spoke / Hub and Spoke model – some discussion last time around using the Hubs for complex cases, Hubs should predominantly be used for the SDA, smaller practices would perhaps not have capacity to see the SDA patients. - DWa asked was this not clarified in spec previously? MG asked for clarification on the hubs and how they are used for the SDA. SEl noted that as Towcester, Brackley and The Parks are probably the bigger areas, Denton and Bugbrooke are the probable outliers. MR working on coordinating room availability within the practices as hubs, so work on this is continuing. This will be shared with the group. ACTION: MR. - EW asked if MR can share a room list with any additional space in Brackley that is needed, whether GMS space or not, it would be appreciated. A request could come from EW on UMF/non-GMS funding, and what can be done to fast track anything, they would be happy to help. - SEl asked for clarification on what the delay was in seeing the contract from ICB and what its current status is? EW has not received this as yet it but should be with her today EW confirmed. The GMS variation element is being drafted, EW not aware of any other issues. SEl noted some turnaround time would be needed by the LMS when the contract is received to be reviewed. EW noted no objection to this being shared as SEl asked for clarification. - AW – Danes Camp and The Parks have rooms that are not GMS funded could these be used? Virtual appointments can be done from anyway it was noted. Patients travelling to a location in terms of travelling to Danes Camp from out of the area of the neighbourhood, would be discouraged as EW confirmed that these should be seen within the neighbourhood area. Complex Care: - MG and RP attended a workshop recently on this. A number of conditions were discussed: COPD – remote monitoring would be available to patients; - Pre-diabetes cohort, would also be a quick win with a text and follow up could be offered as well as offering ongoing support. - Post-discharges following admission back to home – proactively visiting to stave off readmission. - End of life care – better management of patients to allow them to remain at home, with support from primary care. - RP noted that monitoring would allow some improvements and value and agreed with MG as above and this would evolve over time. Populations and data will be looked at by the ICB. - Heart failure could also be looked at. - Muhammed Chishti (MuC) has a particular interest in diabetes and has a specialist clinic to cover this. A Consultant from NGH came to do the MDTs which led to improved outcomes and increased knowledge and skills of doctors and nurses across the PCN. - SEl noted that the acute care funding was discussed with Giles West (GW) this morning. Should GW attend this meeting as he covers the acute funding on the ageing well service as there is some overlap across the SDA and Frailty. Heart failure and remote monitoring also has some overlap with both cohorts. ACTION: MG to invite Giles West to next meeting. - The pre-diabetes cohort was discussed but not agreed as this is probably a longer outcome that can’t be measured within the timeframe of the SDA pilot. - MG asked if there was an agreement on the conditions to be looked: heart failure, hospital discharge, remote monitoring and diabetes. SEaston – requested data before agreeing. Giles West will have this data. Paul Birch – MG to approach for numbers of patients. ACTION: MG to copy EW in an email and ask targeted questions to Paul Birch so he can come back with relevant data. MG noted that the data should be available on the four cohorts agreed (above), for discussion at the next meeting. AOB: - MR gave an update. The technology is being looked at with PM’s, in particular the current telephone system in Denton. They are happy to move system provider. ND is attend MR’s meeting with X-On next week. Could the cost of this come out of the development fund was asked, clarification from EW was sought. MR to feedback to the group at the next meeting on this. ND noted that there will be an early termination fee would be needed (approx.. £7k) but not confirmed. MR would be asking X-On for early termination costs for Denton and would have an idea of this by 23rd December to come back to the next meeting. ACTION: MR - MR is looking at the basic connectivity which will allow access to rotas and allow demo test runs of appointments. This will be started this week. Demo test results are being worked on and worked through. EMIS into SystmOne is being worked on. An update will be given on 23rd December. ACTION: MR - Slot types – EW asked for clarification – SDA / complex care will be differentiated when complete it was agreed. | CG MJG/MG MG MJG EW MG MuC MR MG MG MR MR |
| Next Meeting: Face to face Meeting: Tuesday 23rd December, 12.30 – 2.30 pm, Brackley Medical Centre |  |